## Sheet1
Manual Testing

Test		Public	User	Admin
Home Page	- test all links	06/07/15	06/07/15	06/07/15
History page	- test all links	06/07/15	06/07/15	06/07/15
Publications page	- test all links	06/07/15	06/07/15	06/07/15
Search	- message, registering is required	06/07/15	n/a	n/a
Log in	- fake log-in fails	06/07/15	n/a	n/a
Create or Edit account	- email invalid	06/07/15	06/07/15	06/07/15
	- passwords must match	06/07/15	06/07/15	06/07/15
	- change password, log out and back in	n/a	06/07/15	06/07/15
	- email already registered	06/07/15	06/07/15	06/07/15
	- link "Click here" -> home page	06/07/15	n/a	n/a
	- successfully register	06/07/15	n/a	n/a
Log in or Log out and back in	- success	06/07/15	06/07/15	06/07/15
	- directs to user details page	06/07/15	06/07/15	06/07/15
	- start from top of test sheet as a user	06/07/15	n/a	n/a

Search words “quad”	- definition only, 1 results, back link to "Search" ok		06/07/15	06/07/15
	- sample citations, show headword, 2 citations and "more citations" button		06/07/15	06/07/15
	- all citations, show headword and 4 citations		06/07/15	06/07/15
	- case insensitive "Quad", "QUaD", QUAD" all ok		06/07/15	06/07/15
Search words “quail”	- definition only, 3 results, back link to "Search" ok		06/07/15	06/07/15
	- sample citations, same as "definitions only"		06/07/15	06/07/15
	- all citations, same as "definitions only"		06/07/15	06/07/15
	- test 3 quail links, all go to unique quail entries		06/07/15	06/07/15
All words	- Q has 102 entries, link take to list of 102 entries		06/07/15	06/07/15
	- list alternates grey/white rows, all letter links at top		06/07/15	06/07/15
	- links goto correct and unique headwords		06/07/15	06/07/15
Headword	- Looks ok, headword left, citations right		06/07/15	06/07/15
	- two hover '?' bring up text		06/07/15	06/07/15
	- more citations button brings up more citations		06/07/15	06/07/15
	- back link works		06/07/15	06/07/15

Headword (Admin)	- check links on edit and delete buttons for headword and all citations			06/07/15
	- check links on more and new citations buttons			06/07/15

Headword edit (Admin)	- commit, back link and edit buttons ok			06/07/15
	- headword definition required			06/07/15

New word (Admin)	- page accessed			06/07/15
	- requires non-blank headword and definition			06/07/15
	- all secondary attributes == none is ok			06/07/15
	- all secondary attributes != none is ok			06/07/15

Secondary attributes (Admin)	- Origin listed in alphabetical order			06/07/15
	- edit			06/07/15
	- delete from attribute list			06/07/15
	- create attribute			06/07/15
	- list headwords			06/07/15
	- remove from a specific headword (ie: first 'none' on drop down)			06/07/15
	- create, edit, delete attributes. List headwords: Register			06/07/15
	- remove Register from a specific headword			06/07/15
	- create, edit, delete attributes. List headwords: Flag			06/07/15
	- remove Flag from a specific headword			06/07/15

Citation (Admin)	- create new citation, shows in headword			06/07/15	no date in edit page
	- edit citation, shows in headword			06/07/15	no date in edit page
	- delete citation, confirmation asked			06/07/15
	- Source edit link ok			06/07/15

Citation Source (Admin)	- add new source			06/07/15
	- edit source, archived items drop to bottom of list			06/07/15
	- delete source			06/07/15
	- list headwords using source			06/07/15